## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group F | Completed | 40
Project title |  | In Progress | 0
Stakeholder or organisation | CUT Wellness Centre and Clinic | Not Started | 0
Group mentor |  | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 17 August - 04 September 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 91% | Contribution Summary | Count
Main achievement | Successfully engaged stakeholder, documented requirements, completed SRS, and established project baseline | Contribution entries | 7
Main challenge | Coordinating schedules for all members to attend stakeholder meetings | Verified entries | 7
Next planned activity | System Architecture and Design-Phase 2 | Unverified entries | 0
|  | Stakeholder engagements | 2

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | 2026-08-17 | 2026-08-26 | Completed | 100 | https://teams.microsoft.com/meet/350365753886072?p=QipEIsigoMwE92seOD | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | LD Mokheti ⁠A Jara ⁠TV Thabisi | 2026-08-19 | 2026-08-20 | Completed | 100 | Current process diagram, problem statement part on the document. | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | 2026-08-20 | 2026-08-24 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | LD Mokheti ⁠BF Motseki ⁠A Jara ⁠TV Thabisi | 2026-08-18 | 2026-08-19 | Completed | 100 | Stakeholder Interview document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | LD Mokheti ⁠BF Motseki ⁠A Jara ⁠TV Thabisi | 2026-08-20 | 2026-08-26 | Completed | 100 | Meeting minutes, interview notes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | LD Mokheti A Jara ⁠TV Thabisi | 2026-08-25 | 2026-08-31 | Completed | 100 | SRS document PDF | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | BF Motseki | 2026-08-22 | 2026-08-28 | Completed | 100 | MS Project file | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | S Bila | 2026-08-20 | 2026-08-22 | Completed | 100 | https://github.com/shadrackbila/CampusCare_WIL_Group-F.git | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | B Mbinga ML Mwenda | 2026-08-26 | 2026-08-30 | Completed | 100 | https://nnyrylhpwiakctynylvh.supabase.co/ | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | TV Thabisi | 2026-08-28 | 2026-08-31 | Completed | 100 | Progress Tracker workbook | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | 2026-08-30 | 2026-08-31 | Completed | 100 | Group Reflection section below | Yes |  | Completed
U1-12 | Unit 1 / Phase 1 | Activity 2.1 | Review current Project | A Jara | 2026-08-24 | 2026-08-24 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-13 | Unit 1 / Phase 1 | Activity 2.1 | Evaluate Technical Feasibility | A Jara | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-14 | Unit 1 / Phase 1 | Activity 2.1 | Evaluate Operational Feasibility | A Jara | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-15 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate Economic Feasibility | A Jara | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-16 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate Schedule Feasibility | LD Mokheti | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-17 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate Legal Feasibility | LD Mokheti | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-18 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate Ethical Feasibility | LD Mokheti | 2026-08-24 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-19 | Unit 2 / Phase 1 | Activity 2.1 | Complete the Feasibility Summary | LD Mokheti | 2026-08-27 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-20 | Unit 2 / Phase 1 | Activity 2.1 | Make an Overall Feasibility Decision | LD Mokheti | 2026-08-28 | 2026-08-28 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-21 | Unit 2 / Phase 1 | Activity 2.2 | Identify Project Risks | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-22 | Unit 2 / Phase 1 | Activity 2.2 | Write Clear Risk Statements | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-23 | Unit 2 / Phase 1 | Activity 2.2 | Rate the Likelihood | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-24 | Unit 2 / Phase 1 | Activity 2.2 | Rate the Impact | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-25 | Unit 2 / Phase 1 | Activity 2.2 | Calculate the Risk Score | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-26 | Unit 2 / Phase 1 | Activity 2.2 | Identify a Mitigation Action | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-27 | Unit 2 / Phase 1 | Activity 2.2 | Identify a Contingency Action | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-28 | Unit 2 / Phase 1 | Activity 2.2 | Assign a Risk Owner | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-29 | Unit 2 / Phase 1 | Activity 2.2 | Prepare the Project Risk Register | TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-30 | Unit 2 / Phase 1 | Activity 2.2 | Review the Highest Risks | ⁠TV Thabisi | 2026-08-26 | 2026-08-31 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-31 | Unit 2 / Phase 1 | Activity 2.2 | Update Your Project Records | ⁠BF Motseki,A Jara, ML Mwenda | 2026-08-25 | 2026-08-28 | Completed | 100 | MS Project file,SRS document PDF | Yes |  | Completed
U1-32 | Unit 2 / Phase 1 | Activity 2.3 | Review the Feasibility and Risk Findings | ⁠TV Thabisi | 2026-08-28 | 2026-09-03 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-33 | Unit 2 / Phase 1 | Activity 2.3 | Refine the Project Scope | LD Mokheti | 2026-08-28 | 2026-09-03 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-36 | Unit 2 / Phase 1 | Activity 2.3 | Update the Requirements | LD Mokheti | 2026-08-28 | 2026-09-03 | Completed | 100 | SRS document sections | Yes |  | Completed
U1-37 | Unit 2 / Phase 1 | Activity 2.3 | Update the SRS | LD Mokheti, A Jara | 2026-08-28 | 2026-09-03 | Completed | 100 | SRS document PDF | Yes |  | Completed
U1-38 | Unit 2 / Phase 1 | Activity 2.3 | Update the Microsoft Project Schedule | ⁠BF Motseki,ML Mwenda | 2026-08-28 | 2026-09-03 | Completed | 100 | MS Project file | Yes |  | Completed
U1-39 | Unit 2 / Phase 1 | Activity 2.3 | Update GitHub | S Bila | 2026-08-28 | 2026-09-03 | Completed | 100 | https://github.com/shadrackbila/CampusCare_WIL_Group-F.git | Yes |  | Completed
U1-40 | Unit 2 / Phase 1 | Activity 2.3 | Update the Project Progress Tracker | A Jara ,⁠BF Motseki | 2026-08-28 | 2026-09-03 | Completed | 100 | Project Progress Tracker document | Yes |  | Completed
U1-41 | Unit 2 / Phase 1 | Activity 2.3 | Confirm Important Changes with the Stakeholder | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | 2026-09-03 | 2026-09-03 | Completed | 100 | SRS document PDF | Yes |  | Completed
U1-42 | Unit 2 / Phase 1 | Activity 2.3 | Complete the Phase 1 Group Reflection | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | 2026-09-03 | 2026-09-03 | Completed | 100 | Group Reflection section below | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date, row below]<>"",[Due Date, row below]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
BF Motseki | 223038085 | Unit 1 / Phase 1 | 1.1 ; 1.2 ; 1.3;2.1; 2.2; 2.3 | Stakeholder engagement, process documentation, MS Project creation,Updated MS Project; updated Progress Tracker; confirmed changes with stakeholder; completed group reflection | Created initial MS Project schedule; contributed to stakeholder meetings, problem statement, and requirements documentation;Updated MS Project schedule; updated Progress Tracker; stakeholder confirmation communication; group reflection contributions | 2026-09-01 | 19 | MS Project file; Meeting minutes; SRS contributions;MS Project file; Progress Tracker; Meeting minutes | Yes | 02-09-2026
LD Mokheti | 223051025 | Unit 1 / Phase 1 | 1.1 ; 1.2 ; 1.3; 2,1; 2.3 | Stakeholder engagement, requirements gathering, SRS compilation;Feasibility analysis; scope refinement; SRS updates; stakeholder confirmation; group reflection | Led stakeholder engagement, documented current process, prepared interview questions, conducted interviews, compiled SRS,Evaluated schedule, legal, ethical feasibility; completed feasibility summary/decision; refined scope; updated SRS; confirmed changes with stakeholder; group reflection | 2026-09-01 | 20 | Meeting minutes; Interview guide; SRS document;Feasibility report; SRS document; Scope document; Meeting minutes | Yes | 02-09-2026
A Jara | 223007530 | Unit 1 / Phase 1 | 1.1 ; 1.2 ; 1.3 ;2,1; 2,3 | Stakeholder engagement, requirements gathering, SRS compilation | Participated in stakeholder meetings, contributed to problem statement, scope definition, and SRS;Feasibility analysis; SRS updates; Progress Tracker updates; stakeholder confirmation; group reflection | 01-09-2026 | 19 | Meeting minutes; SRS contributions;Evaluated technical, operational, economic feasibility; updated SRS; updated Progress Tracker; confirmed changes with stakeholder; group reflection | Yes | 02-09-2026
TV Thabisi | 223005893 | Unit 1 / Phase 1 | 1.1 ; 1.2 ; 1.3; 2.2; 2.3 | Stakeholder engagement, progress reporting, coordination ;Complete risk management process; risk register preparation; risk review; group reflection | Coordinated stakeholder engagement, prepared interview questions, documented interview findings, completed progress report and contribution record,Identified risks; wrote risk statements; rated likelihood/impact; calculated risk scores; identified mitigation/contingency actions; assigned risk owners; prepared Risk Register; reviewed highest risks; group reflection | 01-09-2026 | 20 | Meeting minutes; Progress Tracker; Coordination records , Project Risk Register; Risk assessment documentation; Meeting minutes | Yes | 02-09-2026
B Mbinga | 223020021 | Unit 1 / Phase 1 | 1.1; 1,3 ;2.3 | Supabase project setup, Supabase setup; stakeholder confirmation; group reflection | Created and configured initial Supabase project; set up database schema structure, Created initial Supabase project; confirmed changes with stakeholder; contributed to group reflection | 01-09-2026 | 8 | Meeting minutes; Progress Tracker; Coordination records, Supabase project URL; Meeting minutes; Reflection document | Yes | 02-09-2026
S Bila | 223048044 | Unit 1 / Phase 1 | 1.1;1,3;2.3 | GitHub repository setup and configuration, GitHub setup; GitHub updates | Created GitHub repository, configured access for all members, organised project folders, initialised documentation structure ,Created and configured GitHub repository; updated GitHub with latest documentation | 01-09-2026 | 7 | GitHub repository link; Repository structure documentation ,Commit history | Yes | 02-09-2026
ML Mwenda | 221034577 | Unit 1 / Phase 1 | 1.1;1,3;2.3 | Supabase project setup, Supabase setup; records updates; MS Project support | Assisted with Supabase project creation and initial configuration; documented setup process, Assisted with Supabase project setup; updated project records; supported MS Project schedule updates | 31-08-2026 | 7 | Supabase project URL; Setup documentation; Updated records; MS Project file | Yes | 02-09-2026

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-20 | Unit 1 / Phase 1 | Meeting | Kickoff Meeting-Organisation overview, current challenges, and initial requirements gathering | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | Cleo Maluka | The stakeholder provided an overview of CUT Wellness Centre and explained current challenges including manual patient record management, inefficient appointment scheduling, and lack of integrated communication between staff. Initial requirements were gathered including need for mobile and web access, patient management features, and data confidentiality concerns. The project objectives and scope were discussed. | 1. Document and analyse stakeholder requirements. 2. Define project scope and objectives. 3. Prepare initial solution concepts. 4. Schedule follow-up meeting for requirement refinement. | Meeting minutes document
2026-08-26 | Unit 1 / Phase 1 | Online Meeting | Stakeholder project review, requirement refinement, and confidentiality discussion | BF Motseki, LD Mokheti,A Jara, TV Thabisi,B Mbinga, S Bila, ML Mwenda | Cleo Maluka | The stakeholder reviewed and refined initial requirements. The team presented solution ideas including patient registration, appointment scheduling, and record management features. Additional requirements identified: user role management, data encryption, and audit trail. Confidentiality concerns were addressed - the stakeholder emphasised the need for secure access controls. Agreement reached on project scope and priorities for development. | 1. Update requirements based on stakeholder feedback. 2. Incorporate approved features into SRS. 3. Address confidentiality and security requirements. 4. Begin system design phase. | Meeting summary document

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
20-08-2026 | Unit 1 / Phase 1 | Coordinating schedules for all 7 members to attend stakeholder meetings | Not all members could attend both engagement sessions, creating gaps in understanding the project context | Meeting minutes and detailed summaries circulated to all members; recorded meetings for absent members to review | TV Thabisi | 23-08-2026 | Resolved
25-08-2026 | Unit 1 / Phase 1 | SRS compilation taking longer than expected due to iterative refinement with stakeholder | Initial delay in finalising requirements documentation | Additional review sessions scheduled; team prioritised SRS completion; tasks reallocated to ensure timely delivery | LD Mokheti, A Jara | 31-08-2026 | Resolved
28-08-2026 | Unit 1 / Phase 1 | B Mbinga and ML Mwenda had delayed start on Supabase setup | Potential risk for Phase 2 transition | Team reassigned responsibilities; B Mbinga and ML Mwenda started Supabase setup on 26 August; additional support provided by team members | B Mbinga, ML Mwenda | 30-08-2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 17 August - 04 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder engagement (2 meetings with CUT Wellness Centre), current process documentation, problem statement, project aim/objectives/scope, functional and non-functional requirements, SRS document, MS Project schedule, GitHub repository setup, Supabase project setup, and Unit 1 group reflection. | Stakeholder engagement recorded | Yes
What remains incomplete? | All Phase 1 tasks have been completed. Phase 2 (System Architecture and Design) is ready to begin. | Challenges and actions updated | Yes
Why is it incomplete? | N/A - Phase 1 is complete | Group reflection completed | Yes
Which contributions were particularly important? | LD Mokheti's leadership in stakeholder engagement and SRS compilation; BF Motseki's MS Project creation; and the team's collaborative effort in meeting stakeholder requirements. | Microsoft Project updated | Yes
Were there participation concerns? | Some members had limited availability for stakeholder meetings, but all contributed to documentation and task completion. B Mbinga and ML Mwenda started their Supabase tasks later but completed them successfully. | GitHub evidence available | Yes
What will the group improve in the next phase? | 1. Ensure all members review meeting minutes thoroughly. 2. Set stricter deadlines with earlier start dates. 3. Conduct more frequent check-ins. 4. Ensure technical members are engaged earlier in the design process. | Confidential peer check completed | Yes
Main priority for the next phase | System Architecture and Design (Phase 2) - Complete UML diagrams, ERD, Supabase schema design, and interface prototypes.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | 17 August - 04 September 2026 | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most significant learning from Phase 1 was understanding the critical importance of thorough stakeholder engagement in defining a realistic project scope. Our initial assumptions about the clinic's needs evolved significantly after two meetings with stakeholder Cleo Maluka. The kickoff meeting on 20 August provided insight into the clinic's operational challenges, while the follow-up meeting on 26 August refined requirements and addressed data confidentiality concerns. We learned that a software solution must consider not only functional needs but also the stakeholder's context, digital literacy, and security concerns. Additionally, iterative requirement refinement proved valuable—the SRS went through multiple revisions based on stakeholder feedback, preventing misunderstandings and establishing a solid foundation for the design phase. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder engagement was our strongest achievement. We arranged two productive meetings with responsive clinic management who provided valuable operational insights. Collaboration and communication remained consistent through our WhatsApp group and scheduled meetings. The SRS, feasibility analysis, and risk register were compiled to a high standard, incorporating both stakeholder needs and technical considerations. The team successfully completed all Phase 1 tasks within the required timeframe, including MS Project creation, GitHub setup, and Supabase configuration. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Schedule coordination was challenging—not all members could attend both stakeholder meetings due to class or work commitments, creating gaps in understanding. SRS compilation took longer than expected due to iterative refinement after confidentiality concerns were raised. Technical setup for Supabase started later than planned because two members were initially uncertain about the technology, though they completed it successfully with team support. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided by strengths: LD Mokheti led stakeholder engagement and SRS compilation; BF Motseki created the MS Project schedule; A Jara contributed to requirements and SRS; TV Thabisi coordinated reporting; S Bila handled GitHub; B Mbinga and ML Mwenda managed Supabase. While some members were more active in meetings, all contributed meaningfully. The group acknowledges that B Mbinga and ML Mwenda could have engaged earlier but completed their technical tasks successfully. The team commits to more balanced participation in Phase 2.
Did all members contribute fairly? Explain. | Overall, all seven members contributed meaningfully to Phase 1, though the nature and extent of contributions varied. While some members were more visible in stakeholder meetings, all members contributed to the project in meaningful ways. The work was distributed based on individual strengths and availability. The group acknowledges that B Mbinga and ML Mwenda could have been more engaged earlier in the phase, but they completed their assigned technical tasks successfully. The group commits to ensuring more balanced participation in Phase 2.
How did the group handle disagreements or delays? | Disagreements on scope and priorities were resolved through group discussions and reference to stakeholder feedback. For SRS delays, we scheduled additional review sessions. For Supabase delays, we provided technical support and set clear deadlines. Regular check-ins helped identify issues early.
What did the group learn from the stakeholder? | The clinic's patient records are manual and inefficient. Confidentiality is paramount, requiring robust access controls and encryption. User-friendliness is essential given varying staff digital literacy. Dual mobile and web access is necessary as staff work both in-office and remotely.
Improvement action 1 for the next phase | In Phase 2, we will ensure that all group members attend stakeholder meetings or review meeting minutes thoroughly to maintain consistent understanding of requirements. We will schedule meetings at times that accommodate all members and record sessions for those who cannot attend.
Improvement action 2 for the next phase | We will set stricter deadlines for individual tasks and conduct more frequent check-ins to prevent tasks from falling behind schedule. This will include a mid-week progress review and a weekly team meeting to identify and address issues early.
Priority for the next phase | Complete system architecture design, UML diagrams, ERD, Supabase schema, and interface prototypes for Assessment 2.